## Rental Invoicing App
Sl No. | Module | Feature | Sub-Feature | Description | Task to be done | Resource Name | Start Date | End Date | Status
1 | Project Setup & Database (Common) | Project Setup | Requirement walkthrough | Understand the BRD, feature list, user roles and monthly invoice flow | Read the BRD and feature list, clarify doubts with mentor, agree module split | All | 2026-09-17 | 2026-09-17 | Not Started
2 | Project Setup & Database (Common) | Project Setup | Development environment | Tools everyone needs to run the app | Install Python, Node.js, PostgreSQL, Git; run the app locally | All | 2026-09-17 | 2026-09-17 | Not Started
3 | Project Setup & Database (Common) | Project Setup | Code repository & structure | Shared backend and frontend skeleton | Create Git repo, backend (FastAPI) and frontend (React) skeleton, one folder per module | All | 2026-09-18 | 2026-09-18 | Not Started
4 | Project Setup & Database (Common) | Database | Database design | Tables and relationships for all entities | Draw ER diagram: users, landlords, properties, tenants, rental rates, invoices, templates, audit log | All | 2026-09-18 | 2026-09-18 | Not Started
5 | Project Setup & Database (Common) | Database | Table creation | Create all tables in PostgreSQL | Write table scripts with primary/foreign keys and constraints | All | 2026-09-21 | 2026-09-21 | Not Started
6 | Project Setup & Database (Common) | Database | Seed data | Sample data for development and testing | Insert users (1 per role), 3 landlords (GST and Non-GST), 6 properties, 10 tenants, rental rates, 1 invoice template | All | 2026-09-21 | 2026-09-21 | Not Started
7 | Access, Dashboard & Audit | Login & Authentication | Login Screen | Allow Admin, Manager, and Landlord users to log in using registered credentials | Build login API with secure token and the login screen | Priya | 2026-09-22 | 2026-09-22 | Not Started
8 | Access, Dashboard & Audit | Login & Authentication | Role-Based Access Control | Restrict visible screens and actions based on the logged-in user's role (Admin/Manager/Landlord) | Add role checks to every API; show only permitted menus and screens per role | Priya | 2026-09-23 | 2026-09-23 | Not Started
9 | Access, Dashboard & Audit | Login & Authentication | Password Reset | Allow users to reset a forgotten password | Build forgot-password and reset-password screens | Priya | 2026-09-24 | 2026-09-24 | Not Started
10 | Access, Dashboard & Audit | User & Role Management | Create User Account | Admin can create user accounts and assign one of the roles: Admin, Manager, or Landlord | Build user list and create/edit user screen with role selection | Priya | 2026-09-25 | 2026-09-25 | Not Started
11 | Access, Dashboard & Audit | Login & Authentication | Account Activation/Deactivation | Admin can activate or deactivate user accounts | Add activate/deactivate action; block login for inactive users | Priya | 2026-09-25 | 2026-09-25 | Not Started
12 | Access, Dashboard & Audit | User & Role Management | Scope Manager Access | Scope Manager accounts to specific landlords/properties | Build screen to assign landlords/properties to a manager; filter manager data to them | Priya | 2026-09-28 | 2026-09-28 | Not Started
13 | Access, Dashboard & Audit | User & Role Management | Landlord Self-Scoped Access | Automatically scope Landlord accounts to their own data only | Link landlord users to their landlord record; restrict all their data to it | Priya | 2026-09-29 | 2026-09-29 | Not Started
14 | Access, Dashboard & Audit | Dashboard | Logged Role Name | Display the current logged-in user's role | Build dashboard header showing user name and role | Priya | 2026-09-30 | 2026-09-30 | Not Started
15 | Access, Dashboard & Audit | Dashboard | Navigation Cards | Provide navigation cards for key modules (Properties, Landlords, Tenants, Invoices, Reports) | Add cards for Properties, Landlords, Tenants, Invoices and Reports, shown as per role | Priya | 2026-09-30 | 2026-09-30 | Not Started
16 | Access, Dashboard & Audit | Audit & Data Governance | Master Data Change Log | Maintain a change history for master data such as rate changes and landlord GST status changes | Record old/new values, user and time for rate and landlord GST status changes; Admin view screen | Priya | 2026-10-01 | 2026-10-01 | Not Started
17 | Access, Dashboard & Audit | Audit & Data Governance | Automated Data Backup | Perform regular automated backups of master data, invoices, and generated PDFs | Schedule daily database and PDF folder backup; test a restore | Priya | 2026-10-05 | 2026-10-05 | Not Started
18 | Access, Dashboard & Audit | Dashboard | Invoice Status Summary | Display counts of invoices by status (Draft/Generated/Sent) | Show Draft/Generated/Sent counts for the selected month from invoice data | Priya | 2026-10-06 | 2026-10-06 | Not Started
19 | Access, Dashboard & Audit | Audit & Data Governance | Invoice Override Logging | Log any manual override to an invoice before finalization, along with a reason | Record reason, user and changed values when a draft invoice is corrected | Priya | 2026-10-07 | 2026-10-07 | Not Started
20 | Master Data Management | Landlord / Owner Management | Create Landlord | Add a new landlord record capturing PAN, GSTIN, contact, and billing address | Build landlord API and create form with PAN, GSTIN, contact and billing address validations | Subhashini | 2026-09-22 | 2026-09-22 | Not Started
21 | Master Data Management | Landlord / Owner Management | Edit Landlord | Update existing landlord/owner details | Build edit landlord screen with the same validations | Subhashini | 2026-09-23 | 2026-09-23 | Not Started
22 | Master Data Management | Landlord / Owner Management | Deactivate Landlord | Mark a landlord record as Active/Inactive | Add Active/Inactive status; hide inactive landlords from invoicing | Subhashini | 2026-09-23 | 2026-09-23 | Not Started
23 | Master Data Management | Landlord / Owner Management | GST Registration Flag | Flag each landlord as GST-Registered or Non-GST to determine GST applicability on invoices | Add GST Registered switch; GSTIN mandatory only when switched on | Subhashini | 2026-09-24 | 2026-09-24 | Not Started
24 | Master Data Management | Landlord / Owner Management | Assign Default Invoice Template | Assign a default invoice template per landlord, overridable per property | Add template dropdown on landlord form and an override field on property | Subhashini | 2026-09-24 | 2026-09-24 | Not Started
25 | Master Data Management | Property Management | Create Property | Add a new property record with address, type, and total area | Build property API and create form (name, address, type, area) | Subhashini | 2026-09-25 | 2026-09-25 | Not Started
26 | Master Data Management | Property Management | Edit Property | Update existing property details | Build edit property screen | Subhashini | 2026-09-28 | 2026-09-28 | Not Started
27 | Master Data Management | Property Management | Deactivate Property | Mark a property as Active/Inactive (e.g. sold or under renovation) | Add Active/Inactive status | Subhashini | 2026-09-28 | 2026-09-28 | Not Started
28 | Master Data Management | Property Management | Link Property to Landlord | Associate each property with its owning landlord | Add required landlord selection on property form | Subhashini | 2026-09-29 | 2026-09-29 | Not Started
29 | Master Data Management | Landlord / Owner Management | Associate Properties | Associate one or more properties with each landlord | Show and add properties from the landlord details screen | Subhashini | 2026-09-29 | 2026-09-29 | Not Started
30 | Master Data Management | Property Management | Property Listing | View and search the master list of properties | Build property list with search and filters (landlord, type, status) | Subhashini | 2026-09-30 | 2026-09-30 | Not Started
31 | Master Data Management | Tenant Management | Create Tenant | Add a new tenant record capturing PAN, GSTIN (if applicable), and contact details | Build tenant API and create form with PAN, optional GSTIN and contact | Subhashini | 2026-10-01 | 2026-10-01 | Not Started
32 | Master Data Management | Tenant Management | Edit Tenant | Update existing tenant details | Build edit tenant screen | Subhashini | 2026-10-05 | 2026-10-05 | Not Started
33 | Master Data Management | Tenant Management | Deactivate Tenant | Mark a tenant record as inactive/vacated | Add vacate/deactivate action; vacated tenants are not billed | Subhashini | 2026-10-05 | 2026-10-05 | Not Started
34 | Master Data Management | Tenant Management | Link Tenant to Property | Link each tenant to a specific property | Add property selection on tenant form; one active tenant per property | Subhashini | 2026-10-06 | 2026-10-06 | Not Started
35 | Master Data Management | Tenant Management | Lease Date Capture | Capture lease start date and lease end date for each tenant | Add lease start/end dates with validation (end after start) | Subhashini | 2026-10-06 | 2026-10-06 | Not Started
36 | Master Data Management | Tenant Management | Tenant Status Tracking | Maintain tenant status as Active, Notice Period, or Vacated | Add Active / Notice Period / Vacated status and filters on tenant list | Subhashini | 2026-10-07 | 2026-10-07 | Not Started
37 | Rental Rates & Invoicing | Rental Rate Configuration | Define Monthly Rent | Define the base monthly rent amount for a property/tenant combination | Build rental rate API and screen for a tenant/property | Haridharani | 2026-09-22 | 2026-09-22 | Not Started
38 | Rental Rates & Invoicing | Rental Rate Configuration | Additional Recurring Charges | Optionally define additional recurring charges such as maintenance or parking | Add maintenance/parking charge lines to the rate | Haridharani | 2026-09-23 | 2026-09-23 | Not Started
39 | Rental Rates & Invoicing | Rental Rate Configuration | GST Rate Configuration | Define the applicable GST rate where the landlord is GST-registered | Add GST rate field, defaulted from the landlord's GST flag (0 for Non-GST) | Haridharani | 2026-09-23 | 2026-09-23 | Not Started
40 | Rental Rates & Invoicing | Rental Rate Configuration | Effective Date Range | Define effective-from and effective-to dates to support rent revisions over time | Add effective from/to dates and rate history per tenant | Haridharani | 2026-09-24 | 2026-09-24 | Not Started
41 | Rental Rates & Invoicing | Rental Rate Configuration | Overlap Prevention | Prevent overlapping active rates for the same tenant/property | Block rates whose dates overlap an existing rate; show a clear error | Haridharani | 2026-09-25 | 2026-09-25 | Not Started
42 | Rental Rates & Invoicing | Invoice Generation | Select Billing Period | Select the billing month and the landlord(s)/properties to invoice | Build generate-invoices screen: pick month and landlords/properties | Haridharani | 2026-09-28 | 2026-09-28 | Not Started
43 | Rental Rates & Invoicing | Invoice Generation | Auto Rent + GST Calculation | Automatically calculate rent, additional charges, GST (if applicable), and total payable | Write calculation (rent + charges + CGST/SGST or IGST); test with sample data | Haridharani | 2026-09-29 | 2026-09-30 | Not Started
44 | Rental Rates & Invoicing | Invoice Generation | Sequential Invoice Numbering | Auto-generate a unique, sequential invoice number per landlord | Build per-landlord sequential number generator with no duplicates | Haridharani | 2026-10-01 | 2026-10-01 | Not Started
45 | Rental Rates & Invoicing | Invoice Generation | Invoice Status Update | Mark invoice status as Draft, Generated, or Sent | Add Draft > Generated > Sent status changes and status filter | Haridharani | 2026-10-05 | 2026-10-05 | Not Started
46 | Rental Rates & Invoicing | Invoice Generation | Regenerate/Correct Invoice | Support regenerating or correcting an invoice before it is marked final, with an audit trail of changes | Allow editing/regenerating Draft invoices only; write audit entry with reason | Haridharani | 2026-10-06 | 2026-10-06 | Not Started
47 | Invoice Templates & PDF | Invoice Template Management | Configure Business Details | Configure business name, address, and footer text such as bank details and terms | Build template API and form (name, business name, address, footer text) | Ragul | 2026-09-22 | 2026-09-22 | Not Started
48 | Invoice Templates & PDF | Invoice Template Management | Upload Logo | Upload and manage the landlord/business logo shown on invoices | Add logo upload (PNG/JPG, size limit) and display | Ragul | 2026-09-23 | 2026-09-23 | Not Started
49 | Invoice Templates & PDF | Invoice Template Management | Configure Colour Scheme | Configure header and accent colours for the invoice layout | Add header and accent colour pickers | Ragul | 2026-09-24 | 2026-09-24 | Not Started
50 | Invoice Templates & PDF | Invoice Template Management | Template Preview | Preview a template before applying it to live invoices | Build live invoice preview using sample data | Ragul | 2026-09-25 | 2026-09-25 | Not Started
51 | Invoice Templates & PDF | Invoice Template Management | Multiple Templates | Maintain multiple templates and assign a default template per landlord or property | Build template list; support multiple templates and a system default | Ragul | 2026-09-28 | 2026-09-28 | Not Started
52 | Invoice Templates & PDF | PDF Generation & Storage | Generate Invoice PDF | Generate each invoice as a PDF document using the applicable template | Design invoice layout (logo, landlord/tenant details, charges, GST breakup, amount in words) and generate PDF | Ragul | 2026-09-29 | 2026-10-01 | Not Started
53 | Invoice Templates & PDF | PDF Generation & Storage | Store Invoice PDF | Store the generated PDF against the specific tenant, property, and billing period | Save PDFs in folders by landlord/month and link them to invoices | Ragul | 2026-10-05 | 2026-10-05 | Not Started
54 | Invoice Templates & PDF | PDF Generation & Storage | Download Individual PDF | Allow download of individual invoice PDFs | Add download button with role checks | Ragul | 2026-10-06 | 2026-10-06 | Not Started
55 | Invoice Templates & PDF | PDF Generation & Storage | Bulk Download | Allow bulk download of invoice PDFs for a selected period/landlord | Build ZIP download for a selected month/landlord | Ragul | 2026-10-07 | 2026-10-07 | Not Started
56 | Reports | GST Monthly Reporting | Generate GST Summary Report | Generate a monthly GST summary report per landlord showing total taxable value and total GST collected | Build GST report per landlord: taxable value and total GST (Generated/Sent invoices only) | Haridharani | 2026-10-07 | 2026-10-07 | Not Started
57 | Reports | GST Monthly Reporting | Exclude Non-GST Landlords | Exclude Non-GST landlords from GST reporting since no GST is applicable on their invoices | Filter out Non-GST landlords and show a note | Haridharani | 2026-10-07 | 2026-10-07 | Not Started
58 | Reports | GST Monthly Reporting | CGST/SGST/IGST Breakdown | Break down GST collected (CGST/SGST or IGST) to support GST return filing | Add CGST, SGST and IGST columns with totals | Haridharani | 2026-10-08 | 2026-10-08 | Not Started
59 | Reports | GST Monthly Reporting | Export GST Report | Allow export of the GST report in PDF/Excel format for GSTR filing | Add PDF and Excel export | Haridharani | 2026-10-08 | 2026-10-08 | Not Started
60 | Reports | Reports & Outputs | Invoice Register | Display a listing of all invoices generated for a selected period, filterable by landlord, property, or status | Build invoice register with filters, totals and Excel export | Priya | 2026-10-08 | 2026-10-08 | Not Started
61 | Reports | Reports & Outputs | Landlord-Wise Summary Report | Display a consolidated view of total rent invoiced and collected per landlord across all their properties | Build per-landlord totals of rent invoiced (and collected, once payment tracking is agreed) | Ragul | 2026-10-08 | 2026-10-08 | Not Started
62 | Reports | Reports & Outputs | Property Occupancy Summary | Display active vs. vacant properties/tenants for operational tracking (optional) | Build active vs vacant properties/tenants report | Subhashini | 2026-10-08 | 2026-10-08 | Not Started
63 | Testing & Delivery (Common) | Testing | Integration testing | Full flow: Admin setup > Manager generates invoices > Landlord downloads | Test the full flow together and log bugs | All | 2026-10-09 | 2026-10-09 | Not Started
64 | Testing & Delivery (Common) | Testing | Bug fixing | Fix bugs found in testing | Each member fixes bugs in their own module | All | 2026-10-12 | 2026-10-12 | Not Started
65 | Testing & Delivery (Common) | Testing | User acceptance testing | Mentor tests the app as Admin, Manager and Landlord | Run UAT and fix issues | All | 2026-10-13 | 2026-10-13 | Not Started
66 | Testing & Delivery (Common) | Delivery | Deployment & documentation | App running on a server with setup guide | Deploy the app; write README and user guide | All | 2026-10-14 | 2026-10-14 | Not Started
67 | Testing & Delivery (Common) | Delivery | Final demo | Present the app to stakeholders | Each member demos their module | All | 2026-10-15 | 2026-10-15 | Not Started

## HR Agent
Sl No. | Module | Feature | Sub-Feature | Description | Task to be done | Resource Name | Start Date | End Date | Status
1 | Project Setup & Database (Common) | Project Setup | Requirement walkthrough | Understand the BRD, feature list, user roles, chat and approval flows | Read the BRD and feature list, clarify doubts with mentor, agree module split | All | 2026-09-17 | 2026-09-17 | Not Started
2 | Project Setup & Database (Common) | Project Setup | Development environment | Tools and AI access everyone needs | Install Python, Node.js, PostgreSQL (with pgvector), Git; get AI API key | All | 2026-09-17 | 2026-09-17 | Not Started
3 | Project Setup & Database (Common) | Project Setup | Code repository & structure | Shared backend and frontend skeleton | Create Git repo, backend (FastAPI) and frontend (React) skeleton | All | 2026-09-18 | 2026-09-18 | Not Started
4 | Project Setup & Database (Common) | Database | Database design | Tables and relationships for all entities | Draw ER diagram: employees, roles, leave balances, leave/WFH requests, claims, policy documents, grievances, audit log | All | 2026-09-18 | 2026-09-18 | Not Started
5 | Project Setup & Database (Common) | Database | Table creation | Create all tables in PostgreSQL | Write table scripts with keys and constraints; separate secure area for grievance data | All | 2026-09-21 | 2026-09-21 | Not Started
6 | Project Setup & Database (Common) | Database | Seed data | Sample data for development and testing | Insert 20 employees, managers, HR admin, ICC members, leave balances, holidays, sample requests and 5 sample policy documents | All | 2026-09-21 | 2026-09-21 | Not Started
7 | Access & Dashboard | Access & Role Management | Role Management | Manage access based on the user's assigned role. | Build login and roles for Employee, Manager, HR Admin and ICC Member | Jhoshitha | 2026-09-22 | 2026-09-22 | Not Started
8 | Access & Dashboard | Access & Role Management | Role-Based Access | Restrict screens and functions according to user permissions. | Add role checks to every API; show only permitted menus and screens | Jhoshitha | 2026-09-22 | 2026-09-22 | Not Started
9 | Access & Dashboard | Access & Role Management | Employee Access | Allow employees to access their own HR self-service functions and records. | Restrict employees to their own requests and records | Jhoshitha | 2026-09-23 | 2026-09-23 | Not Started
10 | Access & Dashboard | Access & Role Management | Manager Access | Allow managers to access requests from their direct reports. | Show managers only their direct reports' requests | Jhoshitha | 2026-09-23 | 2026-09-23 | Not Started
11 | Access & Dashboard | Access & Role Management | HR Admin Access | Provide HR Admin access to applicable HR management functions. | Give HR Admin access to policies, all requests, reports and users | Jhoshitha | 2026-09-24 | 2026-09-24 | Not Started
12 | Access & Dashboard | Access & Role Management | POSH/ICC Restricted Access | Restrict POSH/grievance information to authorized users. | Allow only ICC members to open POSH/grievance screens and data; test that HR Admin is blocked | Jhoshitha | 2026-09-24 | 2026-09-24 | Not Started
13 | Access & Dashboard | HR Dashboard | Navigation | Provide access to major HR modules. | Build app layout and side menu for all modules | Jhoshitha | 2026-09-25 | 2026-09-25 | Not Started
14 | Access & Dashboard | HR Dashboard | Dashboard | Provide a centralized view of HR self-service information. | Build dashboard page layout | Jhoshitha | 2026-09-25 | 2026-09-25 | Not Started
15 | Access & Dashboard | HR Dashboard | Role-Based Dashboard | Display information according to the user's role and permissions. | Show different dashboard widgets for Employee, Manager, HR Admin and ICC | Jhoshitha | 2026-09-28 | 2026-09-28 | Not Started
16 | Access & Dashboard | HR Dashboard | Request Summary | Display relevant request counts and statuses. | Show request counts by status from leave, WFH and claim data | Jhoshitha | 2026-10-09 | 2026-10-09 | Not Started
17 | AI Assistant & Policy Q&A | Policy Self-Service / RAG | Policy Document Management | Maintain policy title, category, version, audience, effective date and status. | Build policy upload API and admin screen with title, category, version, audience, effective date, status | Vaishali | 2026-09-22 | 2026-09-22 | Not Started
18 | AI Assistant & Policy Q&A | Policy Self-Service / RAG | Policy Index Status | Track the indexing status of policy documents for AI retrieval. | Process uploaded documents into searchable sections; track Pending/Indexed/Failed/Archived | Vaishali | 2026-09-23 | 2026-09-23 | Not Started
19 | AI Assistant & Policy Q&A | Policy Self-Service / RAG | Policy Search | Search the available policy knowledge base for relevant information. | Build semantic search over indexed policy sections | Vaishali | 2026-09-23 | 2026-09-23 | Not Started
20 | AI Assistant & Policy Q&A | Policy Self-Service / RAG | RAG Response | Retrieve relevant policy content and generate an answer. | Generate answers only from retrieved sections; reply 'Information not found in active policies' when unsure | Vaishali | 2026-09-24 | 2026-09-24 | Not Started
21 | AI Assistant & Policy Q&A | Policy Self-Service / RAG | Citation | Define policy document retrieval and AI-based response. | Show document name, section and page with every policy answer | Vaishali | 2026-09-25 | 2026-09-25 | Not Started
22 | AI Assistant & Policy Q&A | Policy Self-Service / RAG | Policy Access Control | Provide policy information according to user permissions. | Filter search results by document audience and user role | Vaishali | 2026-09-25 | 2026-09-25 | Not Started
23 | AI Assistant & Policy Q&A | Policy Self-Service / RAG | Policy Q&A | Allow users to ask questions about HR policies. | Connect policy Q&A to the chat screen; test with 25 sample questions | Vaishali | 2026-09-28 | 2026-09-28 | Not Started
24 | AI Assistant & Policy Q&A | AI Conversational Agent | Conversational Interface | Allow employees to interact with HR services using natural language. | Build chat screen and chat API with message history | Vaishali | 2026-09-29 | 2026-09-29 | Not Started
25 | AI Assistant & Policy Q&A | AI Conversational Agent | Intent Identification | Identify whether the user request is informational or transactional. | Classify each message as a policy question or a request (leave, WFH, claim, grievance) | Vaishali | 2026-09-29 | 2026-09-29 | Not Started
26 | AI Assistant & Policy Q&A | AI Conversational Agent | Entity Extraction | Extract required information such as dates, request type, amount and reason. | Extract dates, request type, amount and reason from messages | Vaishali | 2026-10-05 | 2026-10-05 | Not Started
27 | AI Assistant & Policy Q&A | AI Conversational Agent | Missing Information | Ask follow-up questions when required information is missing. | Ask follow-up questions until all required details are captured | Vaishali | 2026-10-05 | 2026-10-05 | Not Started
28 | AI Assistant & Policy Q&A | AI Conversational Agent | Input Validation | Validate captured information against applicable business rules. | Check captured details against rules (balance, dates, claim limits) before confirmation | Vaishali | 2026-10-06 | 2026-10-06 | Not Started
29 | AI Assistant & Policy Q&A | AI Conversational Agent | Request Confirmation | Show captured details and obtain user confirmation before submission. | Show a confirmation card with all details; nothing is submitted without the user's click | Vaishali | 2026-10-06 | 2026-10-06 | Not Started
30 | AI Assistant & Policy Q&A | AI Conversational Agent | Transaction Submission | Create the appropriate HR transaction after confirmation. | Create the leave/WFH/claim request after confirmation and show the request ID | Vaishali | 2026-10-07 | 2026-10-07 | Not Started
31 | Leave, WFH & Reimbursement | Leave & WFH | Leave Request | Allow employees to submit leave requests. | Build leave request API and form | Vaishali | 2026-09-30 | 2026-09-30 | Not Started
32 | Leave, WFH & Reimbursement | Leave & WFH | Leave Details | Capture leave type, dates, duration, day type and reason. | Capture leave type, dates, duration, half/full day and reason | Vaishali | 2026-09-30 | 2026-09-30 | Not Started
33 | Leave, WFH & Reimbursement | Leave & WFH | WFH Request | Allow employees to submit work-from-home requests. | Build WFH request API and form | Vaishali | 2026-10-01 | 2026-10-01 | Not Started
34 | Leave, WFH & Reimbursement | Leave & WFH | Date Validation | Validate request dates and duration. | Validate dates, count working days (skip weekends/holidays) and check leave balance | Vaishali | 2026-10-01 | 2026-10-01 | Not Started
35 | Leave, WFH & Reimbursement | Leave & WFH | Manager Approval | Route applicable requests to the employee's manager. | Route leave/WFH requests to the employee's reporting manager | Vaishali | 2026-10-07 | 2026-10-07 | Not Started
36 | Leave, WFH & Reimbursement | Leave & WFH | Request Status | Track submitted, approved and rejected requests. | Build My Requests screen with Submitted/Approved/Rejected status | Vaishali | 2026-10-08 | 2026-10-08 | Not Started
37 | Leave, WFH & Reimbursement | Reimbursement | Claim Submission | Allow employees to submit expense reimbursement claims. | Build expense claim API and form | Vaishali | 2026-10-08 | 2026-10-08 | Not Started
38 | Leave, WFH & Reimbursement | Reimbursement | Claim Details | Capture category, expense date, amount, and receipt. | Capture category, expense date, amount and receipt | Vaishali | 2026-10-08 | 2026-10-08 | Not Started
39 | Leave, WFH & Reimbursement | Reimbursement | Receipt Attachment | Store the receipt associated with a reimbursement claim. | Upload and store the receipt (JPG/PNG/PDF) against the claim | Vaishali | 2026-10-09 | 2026-10-09 | Not Started
40 | Leave, WFH & Reimbursement | Reimbursement | Claim Validation | Validate required information and claim amount. | Check required fields, amount and 30-day submission limit | Vaishali | 2026-10-09 | 2026-10-09 | Not Started
41 | Leave, WFH & Reimbursement | Reimbursement | Manager Approval | Route applicable claims to the designated approver. | Route claims to the designated approver | Vaishali | 2026-10-09 | 2026-10-09 | Not Started
42 | Leave, WFH & Reimbursement | Reimbursement | Approval Status | Track the status of reimbursement claims. | Show claim status Pending Review > Approved/Rejected > Settled | Vaishali | 2026-10-12 | 2026-10-12 | Not Started
43 | POSH / Grievance | POSH / Grievance | Confidential Intake | Provide a protected process for submitting POSH/grievance cases. | Build confidential report form with disclaimer, separate from chat history | Jhoshitha | 2026-10-05 | 2026-10-05 | Not Started
44 | POSH / Grievance | POSH / Grievance | Anonymous Complainant | Support anonymous complainant information where applicable. | Add named/anonymous choice; do not store identity when anonymous | Jhoshitha | 2026-10-05 | 2026-10-05 | Not Started
45 | POSH / Grievance | POSH / Grievance | Case Information | Capture respondent, incident date/period, location/channel, description and evidence. | Capture respondent, incident date/period, location/channel, description and evidence files | Jhoshitha | 2026-10-06 | 2026-10-06 | Not Started
46 | POSH / Grievance | POSH / Grievance | Data Encryption | Protect sensitive POSH/grievance data using the required encryption approach. | Encrypt description and evidence before saving; verify the database holds only encrypted text | Jhoshitha | 2026-10-06 | 2026-10-06 | Not Started
47 | POSH / Grievance | POSH / Grievance | Restricted Data | Restrict access to sensitive POSH/grievance information. | Store POSH data separately; only ICC members can read it | Jhoshitha | 2026-10-07 | 2026-10-07 | Not Started
48 | POSH / Grievance | POSH / Grievance | ICC Case Officer | Associate an authorized ICC case officer with the case. | Build ICC case screen with case officer assignment | Jhoshitha | 2026-10-07 | 2026-10-07 | Not Started
49 | POSH / Grievance | POSH / Grievance | Case Status | Track the status of a POSH/grievance case. | Add status flow Received > Formal Inquiry > Actioned > Closed | Jhoshitha | 2026-10-07 | 2026-10-07 | Not Started
50 | POSH / Grievance | POSH / Grievance | AI Intake & Routing | Use AI for intake and routing while investigation remains human-led. | Detect grievance messages in chat and hand off to the confidential form; AI makes no decision on the case | Vaishali | 2026-10-12 | 2026-10-12 | Not Started
51 | Approvals, Reports & Audit | Approval Workflow | Approve Request | Allow an authorized approver to approve a submitted request. | Build approval queue and approve action for leave, WFH and claims | Jhoshitha | 2026-09-29 | 2026-09-29 | Not Started
52 | Approvals, Reports & Audit | Approval Workflow | Reject Request | Allow an authorized approver to reject a submitted request. | Add reject action with mandatory comment | Jhoshitha | 2026-09-29 | 2026-09-29 | Not Started
53 | Approvals, Reports & Audit | Approval Workflow | Approver Action Tracking | Record approval or rejection actions for audit purposes. | Save approver, action, comment and time on each request | Jhoshitha | 2026-09-30 | 2026-09-30 | Not Started
54 | Approvals, Reports & Audit | Audit Logging | User & Timestamp | Record the user ID and timestamp for auditable actions. | Build audit log table and service capturing user ID and time | Jhoshitha | 2026-09-30 | 2026-09-30 | Not Started
55 | Approvals, Reports & Audit | Audit Logging | Entity Tracking | Record the affected entity type and entity ID. | Record entity type and entity ID for each audit entry | Jhoshitha | 2026-10-01 | 2026-10-01 | Not Started
56 | Approvals, Reports & Audit | Audit Logging | Immutable Audit Trail | Maintain an immutable audit record for applicable transactions. | Make audit entries insert-only (no update/delete) and verify | Jhoshitha | 2026-10-01 | 2026-10-01 | Not Started
57 | Approvals, Reports & Audit | Audit Logging | Prompt Logging | Record prompt text associated with applicable AI transactions. | Log chat prompt text for AI transactions (never for POSH) | Jhoshitha | 2026-10-08 | 2026-10-08 | Not Started
58 | Approvals, Reports & Audit | Audit Logging | Parameter Logging | Record extracted transaction parameters. | Log extracted parameters (dates, type, amount, reason) | Jhoshitha | 2026-10-08 | 2026-10-08 | Not Started
59 | Approvals, Reports & Audit | Audit Logging | Approver Action | Record the approver action associated with a transaction. | Log approve/reject actions into the audit trail | Jhoshitha | 2026-10-08 | 2026-10-08 | Not Started
60 | Approvals, Reports & Audit | Reports | Leave/WFH Report | Provide reports on leave and WFH requests and their statuses. | Build leave/WFH report with filters and Excel export | Jhoshitha | 2026-10-09 | 2026-10-09 | Not Started
61 | Approvals, Reports & Audit | Reports | Reimbursement Report | Provide reports on reimbursement claims and their statuses. | Build claims report with filters and Excel/CSV export | Jhoshitha | 2026-10-09 | 2026-10-09 | Not Started
62 | Approvals, Reports & Audit | Reports | POSH/Grievance Report | Provide authorized reporting on POSH/grievance cases. | Build ICC-only report: case counts, status and days to close, no personal details | Jhoshitha | 2026-10-12 | 2026-10-12 | Not Started
63 | Approvals, Reports & Audit | Reports | HR Operational Summary | Provide relevant operational summaries for authorized HR users. | Build HR Admin summary: request volumes and average approval time | Jhoshitha | 2026-10-12 | 2026-10-12 | Not Started
64 | Testing & Delivery (Common) | Testing | Integration testing & bug fixing | Full flow: policy question > leave via chat > claim > approval > grievance | Test the full flow together; fix bugs | All | 2026-10-13 | 2026-10-13 | Not Started
65 | Testing & Delivery (Common) | Testing | User acceptance testing | Mentor tests as Employee, Manager, HR Admin, ICC member | Run UAT and fix issues | All | 2026-10-14 | 2026-10-14 | Not Started
66 | Testing & Delivery (Common) | Delivery | Deployment, documentation & demo | App running on a server; setup guide; final presentation | Deploy, write README and user guide, demo to stakeholders | All | 2026-10-15 | 2026-10-15 | Not Started